TASKS

- Hardware and Initial setup

| Main Task (Epic) | Subtasks (Action Items) | Dependencies | Notes | Man day |
| --- | --- | --- | --- | --- |
| HS-1: Project & Peripherals Setup | HS-1.1: Set up STM32CubeIDE project. | None | Use STM32F207ZG target. | 0.5 |
|  | HS-1.2: Configure clock tree (HSE, PLL). |  |  | 0.5 |
|  | HS-1.3: Configure I2C/SPI for sensor communication (HAL). |  |  | 0.5 |
|  | HS-1.4: Configure GPIO pins for LEDs (HAL). |  |  | 0.5 |
|  | HS-1.5: Configure Ethernet MAC and related GPIOs (HAL). |  |  | 1 |
|  | HS-1.6: Initialize Timer (TIM) for system tick/RTOS (HAL). |  |  | 1.5 |

- Core Drivers and RTOS Integration

| Main Task (Epic) | Subtasks (Action Items) | Dependencies | Notes | Man day |
| --- | --- | --- | --- | --- |
| DRV-1: Integrate FreeRTOS | DRV-1.1: Integrate FreeRTOS into the project. | HS-1.6 |  | 1 |
|  | DRV-1.2: Create initialization task and start the scheduler. |  |  | 1 |
| DRV-2: PAJ7660 Sensor Driver | DRV-2.1: Implement sensor power-up and basic I2C/SPI initialization sequence. | HS-1.3 |  | 1.5 |
|  | DRV-2.2: Configure sensor to operate in the required Gesture Mode 5. |  |  | 1 |
|  | DRV-2.3: Implement read_gesture_id() function (Layer 3 output). | DRV-2.2 | Reads the classified integer. | 1.5 |
| DRV-3: LED Driver | DRV-3.1: Implement set_led(pin, state) utility function. | HS-1.4 |  | 0.5 |
|  | DRV-3.2: Implement set_leds_by_count(int count) using the utility. | DRV-3.1 | Controls the 5-LED output. | 0.5 |
| DRV-4: Networking Stack (LWIP) | DRV-4.1: Integrate LWIP library with the Ethernet MAC HAL. | HS-1.5 |  | 1.5 |
|  | DRV-4.2: Configure LWIP for DHCP address acquisition. |  |  | 1.5 |
|  | DRV-4.3: Implement a basic PING test to verify network connectivity. | DRV-4.2 | Debugging check. | 0.5 |

- Application Logic and Feature Implementation

| Main Task (Epic) | Subtasks (Action Items) | Dependencies | Notes | Man day |
| --- | --- | --- | --- | --- |
| APP-1: Sensing Task | APP-1.1: Create RTOS task for continuous sensor polling | DRV-1, DRV-2.3 |  | 1 |
|  | APP-1.2: Map the sensor's raw IDs to the 5 standard system gestures (e.g., ID 8 → Swipe Left). | APP-1.1 |  | 1 |
| APP-2: Local Feedback | APP-2.1: Receive Gesture ID from APP-1.2. | APP-1.2 |  | 0.5 |
|  | APP-2.2: Call DRV-3.2 to immediately display N LEDs for Gesture ID N. | DRV-3.2 | Low-latency path. | 0.5 |
| APP-3: MQTT Client & Payload | APP-3.1: Integrate lightweight MQTT client library | DRV-4.3 |  | 2 |
|  | APP-3.2: Implement MQTT connection and authentication logic. | APP-3.1 | Handles reconnects. | 1.5 |
|  | APP-3.3: Implement payload struct: Gesture_ID, Timestamp, Status. | APP-3.1 |  | 1 |
|  | APP-3.4: Implement QoS 1 publish logic (requires acknowledgement). | APP-3.3 | PRD requirement for reliability. | 2.5 |
| APP-4: Failsafe & Monitoring | APP-4.1: Initialize and periodically feed the Watchdog Timer. | DRV-1 | Ensures system restart on crash. | 0.5 |
|  | APP-4.2: Monitor sensor read status and network connection status. | DRV-2.3, DRV-4.2 |  | 0.5 |
|  | APP-4.3: Implement the Failsafe Visual Alert (blink all 5 LEDs) if status check fails. | DRV-3.2, APP-4.2 |  | 0.5 |

- Quality Assurance and Documentation

| Main Task (Epic) | Subtasks (Action Items) | Dependencies | Notes | Man day |
| --- | --- | --- | --- | --- |
| QA-1: Performance Testing | QA-1.1: Set up timing hooks around sensor read and MQTT publish acknowledgment. | APP-2, APP-3.4 |  | 1.5 |
|  | QA-1.2: Execute 100 test gestures and calculate average latency. | QA-1.1 | Verify $\le 200 \text{ms}$ cap. | 1 |
| QA-2: Reliability Testing | QA-2.1: Stress test MQTT QoS 1 delivery during simulated network disconnects. | APP-3.4, APP-4.3 |  | 1.5 |
|  | QA-2.2: Verify Emergency Stop (Closed Fist) response time. | APP-2.2 | Needs defined priority. | 0.5 |
| DOC-1: Finalizing Documentation | DOC-1.1: Document the final MQTT topic structure and JSON/binary payload. | APP-3.3 |  | 0.5 |
|  | DOC-1.2: Update the architectural diagram and component descriptions to reflect the PAJ7660 integration. | Final QA |  | 0.5 |