## create an excel sheet with the
Sprint | Task ID | User Story ID | Task Description | Assignee | Priority | Estimated MD | Remaining MD | Status | Notes
1 | PS-1.1 | PS-1 | Set up STM32CubeIDE project. | Anusree | High | 1 | 0 | Done | Use STM32F207ZG target.
1 | PS-1.2 | PS-1 | Configure clock tree (PSE, PLL). | Anusree | High |  |  | Done |  | Low | To Do
1 | PS-1.3 | PS-1 | Configure I2C for sensor communication (HAL). | Anusree | High |  |  | Done |  | Medium | In Progress
1 | PS-1.4 | PS-1 | Configure GPIO pins for LEDs (HAL) and interrupt pin. | Anusree | High |  |  | Done |  | High | Done
| PS-1.5 | PS-1 | Configure Debug UART, with 921600/115200 | Anusree | Medium |  |  | Done
| PS-1.6 | PS-1 | Configure Ethernet MAC and related GPIOs (HAL). |  | High |  |  | To Do
| PS-1.7 | PS-1 | Initialize Timer (TIM) for system tick/RTOS (HAL). |  |  |  |  | To Do |  | Jyothish
|  |  | Integrate FreeRTOS into the project. |  |  |  |  | To Do |  | Anusree
|  |  | Create initialization task and start the scheduler. |  |  |  |  | To Do
|  |  | Debug print framework | Anusree | High | 2
| DRV-2.1 | DRV-2 | Implement sensor power-up and basic I2C initialization sequence. | Jyothish | High | 1 | 0 | Done
| DRV-2.2 | DRV-2 | Configure sensor to operate in the required Gesture Mode. | Jyothish | High | 1 |  | In Progress
| DRV-2.3 | DRV-2 | Implement read_gesture_id() function with stable state & Debug print. | Jyothish | High | 2.5 |  | To Do | Reads the classified integer.
| DRV-3.2 | DRV-3 | Implement gesture_feedback(state gesture) using the utility. | Anusree | High | 1.5 |  | To Do | Controls the 5-LED output.
| DRV-4.1 | DRV-4 | Integrate LWIP library with the Ethernet MAC HAL. |  |  |  |  | To Do
| DRV-4.2 | DRV-4 | Configure LWIP for DHCP address acquisition. |  |  |  |  | To Do
| DRV-4.3 | DRV-4 | Implement a basic PING test to verify network connectivity. |  |  |  |  | To Do | Debugging check.
| APP-1.1 | APP-1 | Create RTOS task for continuous sensor polling |  |  |  | 1 | To Do
| APP-1.2 | APP-1 | Map the sensor's raw IDs to the 5 standard system gestures (e.g., ID 8 → Swipe Left). |  |  |  | 1 | To Do
| APP-2.1 | APP-2 | Receive Gesture ID from APP-1.2. |  |  |  | 0.5 | To Do
| APP-2.2 | APP-2 | Call DRV-3.2 to immediately display N LEDs for Gesture ID N. |  |  |  | 0.5 | To Do | Low-latency path.
| APP-3.1 | APP-3 | Integrate lightweight MQTT client library |  |  |  | 2 | To Do
| APP-3.2 | APP-3 | Implement MQTT connection and authentication logic. |  |  |  | 1.5 | To Do | Handles reconnects.
| APP-3.3 | APP-3 | Implement payload struct: Gesture_ID, Timestamp, Status. |  |  |  | 1 | To Do
| APP-3.4 | APP-3 | Implement QoS 1 publish logic (requires acknowledgement). |  |  |  | 2.5 | To Do | PRD requirement for reliability.
| APP-4.1 | APP-4 | Initialize and periodically feed the Watchdog Timer. |  |  |  | 0.5 | To Do | Ensures system restart on crash.
| APP-4.2 | APP-4 | Monitor sensor read status and network connection status. |  |  |  | 0.5 | To Do
| APP-4.3 | APP-4 | Implement the Failsafe Visual Alert (blink all 5 LEDs) if status check fails. |  |  |  | 0.5 | To Do
| QA-1.1 | QA-1 | Set up timing hooks around sensor read and MQTT publish acknowledgment. |  |  |  | 1.5 | To Do
| QA-1.2 | QA-1 | Execute 100 test gestures and calculate average latency. |  |  |  | 1 | To Do | Verify ≤200ms cap.
| QA-2.1 | QA-2 | Stress test MQTT QoS 1 delivery during simulated network disconnects. |  |  |  | 1.5 | To Do
| QA-2.2 | QA-2 | Verify Emergency Stop response time. |  |  |  | 0.5 | To Do | Needs defined priority.
| DOC-1.1 | DOC-1 | Document the final MQTT topic structure and JSON/binary payload. |  |  |  | 0.5 | To Do
| DOC-1.2 | DOC-1 | Update the architectural diagram and component descriptions to reflect the PAJ7660 integration. |  |  | 0.5 | 0.5 | To Do
Abbreviations
| PS | Platform Setup
| DRV | Driver and RTOS integration
| APP | Application
| QA | Quality Assurance